## Slide 1
Project Card — Single Project
Effect of Curb Extensions | University of Pennsylvania | Erick Guerra | Project 579
Status
WHAT
Objective: This project the effects of curb extensions on traffic safety through their implementation as part of a stormwater management program in the City of Philadelphia.
Research Priority: Traffic safety
Approach: This project employs Bayesian negative binomial models to compare collisions across a set of treated intersections and control intersections which have been identified for future treatment.
Partners: The City of Philadelphia’s Office of Transportation and Infrastructure Systems and Water Department
STATUS
% Complete: 100%
Budget Allocated: $180,000
Budget Spent: $180,000
Next Milestone: Add to FHWA CMF clearinghouse
WHY IT MATTERS
Although widely deployed to promote traffic safety, the effects of curb extensions on traffic safety are poorly understood. The Federal Highway Administration has identified research into the effects of curb extensions on crashes as a high priority area for empirical research
Outcome / relevance: . Analysis suggested that curb extensions reduced the incidence of reported crashes by around 13% at a typical intersection.
Tech Transfer
Type: Implementation
Barriers: Funding to treat multiple corners at each intersection
Partners: City of Philadelphia
Visibility Status for Leadership
Pictures, figures, diagrams, and other relevant visuals may go in this white space.
Federal Share: $90,000
Non-federal Share: $90,000

## Slide 2
Project Deep Dive
Project Title | University | PI | Project ID
TIMELINE
Data collection and processing: completed 11/1/2025
Published in Transportation Research Record: date / status
Schedule note if needed
BUDGET
Allocated: $180,000
Spent: $180,000
Burn %: 100%
DELIVERABLES
Final report: completed
Publication: completed
Inclusion in FHWA CMF clearing house: ongoing
Report and publication completed with ongoing work to disseminate findings and work with research partners.
RISKS / NOTES
Risk: Nothing to report
Mitigation: Nothing to report
Decision request if needed
Keep this slide factual. If a detail does not drive a decision, it should not be here.